## IGCE Totals
Total Projected Costs of Project |  | Sample only, rates are arbitrary
Task Order Title
Prepared Date
Prepared By
|  | Basis of Estimate | Average Rates
| Base Period (3 mos) | Option Period 1 (12 mos) | Option Period 2 (12 mos) | Option Period 3 (12 mos) | Option Period 4 (12 mos) | Contract Total
Labor (DevOps) | 1508000 | 1666560 | 1716556.8 | 1768053.504 |  | 6659170.304 | Base Period rates are linked to Agile Estimator
Labor (Help Desk) |  | 1951960 | 2010518.8 | 2070834.364 |  | 6033313.164
Travel | 50000 | 50000 | 50000 | 50000 |  | 200000 | Option Period rates include estimated 3% increase
Materials | 10000 | 10000 | 10000 | 10000 |  | 40000
Total | 1568000 | 3678520 | 3787075.6 | 3898887.868 | 0 | 12932483.468
Optional Tasks | 2320000 | 0 | 0 | 0 | 0 | 2320000
Total w/Optional Tasks | 3888000 | 3678520 | 3787075.6 | 3898887.868 | 0 | 15252483.468

## DEV - 3 Mos
Sample Development Team - 3 month project
| Iteration: Scrum Sprint | Factor | Labor Category | Hr Rate | Hrs per Iteration | Price | Iteration: Scrum Sprint | Factor
| Size of Team | 11 | Program Manager | 100 | 20 | 2000 | Team Price | 116000
| # of Teams | 1 | Product Manager | 200 | 80 | 16000 | # of Teams | 1
| Types of Iterations | Development | Scrum Master | 100 | 80 | 8000 | Total Iterations Required | 13
| Weeks per Iteration | 2 | DevOps Engineer, Senior | 150 | 160 | 24000 | Price Estimate | 1508000
| Period of Performance (months) | 3 | Back-end Engineer, Senior | 200 | 80 | 16000 | Fee Estimate | 0
| Fee Percentage | 0% | Front-end Engineer, Senior | 150 | 80 | 12000 | Total Price | 1508000
|  |  | User Experience Researcher | 100 | 80 | 8000
|  |  | UX Designer | 100 | 80 | 8000 | Travel | 50000
|  |  | Content Writer | 200 | 80 | 16000 | Materials | 10000
|  |  | Documentation Specialist | 150 | 40 | 6000 | Total ODCs | 60000
0
[6 empty] | 0 | IGCE Total | 1568000
|  |  | Price per team |  |  | 116000
Optional Tasks:
|  |  | # of Sprints | Cost of Team | Total
|  |  | 20 | 116000 | 2320000
Iteration Planner
Team Planner
Government Estimate

## DevOps - 12 Mos
Sample DevOps Team - 12 month project
| Iteration: Scrum Sprint | Factor | Labor Category | Hr Rate | Hrs per Iteration | Price | Iteration: Scrum Sprint | Factor
| Size of Team | 8 | Program Manager | 100 | 40 | 4000 | Team Price | 64000
| # of Teams | 1 | Product Manager | 200 | 80 | 16000 | # of Teams | 1
| Types of Iterations | DevOps | Scrum Master | 100 | 80 | 8000 | Total Iterations Required | 26.04
| Weeks per Iteration | 2 | DevOps Engineer, Senior | 150 | 80 | 12000 | Price Estimate | 1666560
| Period of Performance (months) | 12 | DevOps Engineer, Junior | 150 | 80 | 12000 | Fee Estimate | 0
| Fee Percentage | 0% | Content Strategist | 200 | 40 | 8000 | Total Price | 1666560
|  |  | User Experience Researcher | 100 | 20 | 2000
|  |  | UX Designer | 100 | 20 | 2000 | Travel | 20000
[7 empty] | Materials | 30000
[6 empty] | 0 | Total ODCs | 50000
0
[6 empty] | 0 | IGCE Total | 1716560
|  |  | Price per team |  |  | 64000
Optional Tasks:
|  |  | # of Sprints | Cost of Team | Total
|  |  | 0 | 64000 | 0
Iteration Planner
Team Planner
Government Estimate

## Helpdesk
Sample Helpdesk Team - 12 month project
| Iteration: Scrum Sprint | Factor | Labor Category | Hr Rate | Hrs per Iteration | Price | Iteration: Scrum Sprint | Factor
| Size of Team | 6 | Program Manager | 100 | 10 | 1000 | Team Price | 37000
| # of Teams | 2 | Product Manager | 200 | 40 | 8000 | # of Teams | 2
| Types of Iterations | DevOps | Technical Support II | 100 | 80 | 8000 | Total Iterations Required | 26.04
| Weeks per Iteration | 2 | Technical Support | 100 | 160 | 16000 | Price Estimate | 1926960
| Period of Performance (months) | 12 | Technical Training Specialist | 100 | 40 | 4000 | Fee Estimate | 0
| Fee Percentage | 0% |  |  |  |  | Total Price | 1926960
[7 empty] | Travel | 0
[7 empty] | Materials | 25000
[7 empty] | Total ODCs | 25000
0
[6 empty] | 0 | IGCE Total | 1951960
|  |  | Price per team |  |  | 37000
Optional Tasks:
|  |  | # of Sprints | Cost of Team | Total
|  |  |  | 37000 | 0
Iteration Planner
Team Planner
Government Estimate

## Average Rates
Accessibility Expert | 200 | These rates are not what the gov uses for IGCE
Accessibility Specialist | 200
Administrative Support | 100
Back-end Engineer | 200
Back-end Engineer, Senior | 200
Business Analyst | 200
Business Analyst, Senior | 200
Content Strategist | 200
Content Strategy Lead | 200
Content Writer | 200
Data Analytics Engineer | 200
Data Analytics Engineer, Senior | 200
Data Migration Architect | 200
Data Scientist | 200
Database Administrator | 150
DevOps Engineer | 150
DevOps Engineer, Junior | 150
DevOps Engineer, Senior | 150
Documentation Specialist | 150
Front-end Engineer | 150
Front-end Engineer, Senior | 150
Full Stack Developer | 150
Product Manager | 200
Program Manager | 100
Scrum Master | 100
Software Engineer | 200
Technical Support | 100
Technical Support II | 100
Technical Support III | 100
Technical Training Specialist | 100
Technical Training Specialist, Senior | 100
Test Automation Engineer | 100
User Experience Lead | 100
User Experience Researcher | 100
User Experience Researcher, Senior | 100
UX Designer | 100